## -
Thesis planning
Subject | Optimization and hedging of liability-driven investment portfolios under Wtp: earning the protection return
Uni supervisor | Johan van Leeuwaarden |  |  | Deadline passed
Company supervisor | Roel Mehlkopf |  |  | In progress
Start date | 2026-09-23 |  |  | Achieved
Final date | 2027-04-23
Week | Weekindeling | Thesis werkzaamheden | Deadlines
Week 39: 21 Sep-25 Sep | ma, wo, do: Collateral di, vr: Thesis | Brainstorming onderzoeksrichting, proposal opstellen | Proposal
Week 40: 28 Sep-2 Oct | ma, wo, do: Collateral di, vr: Thesis | Papers Lezen + Base Case model
Week 41: 5 Oct-9 Oct | ma, wo, do: Collateral di, vr: Thesis 8 okt 10.00 JvL | Papers Lezen + Base Case model | Base Case Model
Week 42: 12 Oct-16 Oct | ma, wo, do: Collateral di, vr: Thesis | Papers Lezen
Week 43: 19 Oct-23 Oct | ma, do: Collateral di, wo, vr: Thesis | Papers Lezen + Model bouwen | Probleemomschrijving
Week 44: 26 Oct-30 Oct | ma, do: Collateral di, wo, vr: Thesis | Papers Lezen + Model bouwen
Week 45: 2 Nov-6 Nov | ma, do: Collateral di, wo, vr: Thesis | Papers Lezen + Model bouwen
Week 46: 9 Nov-13 Nov | ma, do: Collateral di, wo, vr: Thesis | Papers Lezen + Model bouwen | Literatuurstudie
Week 47: 16 Nov-20 Nov | ma, do: Collateral di, wo, vr: Thesis | Model bouwen
Week 48: 23 Nov-27 Nov | ma, do: Collateral di, wo, vr: Thesis | Model bouwen
Week 49: 30 Nov-4 Dec | ma, do: Collateral di, wo, vr: Thesis | Model bouwen | Plan van aanpak
Week 50: 7 Dec-11 Dec | ma, do: Collateral di, wo, vr: Thesis | Model bouwen
Week 53: 28 Dec-1 Jan | ma, do: Collateral di, wo, vr: Thesis | Model bouwen
Week 1: 4 Jan-8 Jan | ma, do: Collateral di, wo, vr: Thesis | Model bouwen | Model finalizeren
Week 2: 11 Jan-15 Jan |  | Wintersport - Ischgl | Km's maken / bier drinken
Week 3: 18 Jan-22 Jan | ma, do: Collateral di, wo, vr: Thesis | Resultaten + Verslag
Week 4: 25 Jan-29 Jan | ma, do: Collateral di, wo, vr: Thesis | Resultaten + Verslag | Onderzoeksresulaten
Week 5: 1 Feb-5 Feb | ma, do: Collateral di, wo, vr: Thesis | Afronden verslag + Voorbereiding verdediging | Introductie
Week 6: 8 Feb-12 Feb | ma, do: Collateral di, wo, vr: Thesis | Afronden verslag + Voorbereiding verdediging | Conclusie & Aanbevelingen
Week 7: 15 Feb-19 Feb | ma, do: Collateral di, wo, vr: Thesis | Verdediging/Eindpresentatie | Inleveren verslag
Week 8: 22 Feb-26 Feb | ma, do: Collateral di, wo, vr: Thesis | Verdediging/Eindpresentatie
Week 9: 1 Mar-5 Mar
Week 10: 8 Mar-12 Mar
Week 11: 15 Mar-19 Mar
Week 12: 22 Mar-26 Mar
Week 13: 29 Mar-2 Apr
Week 14: 5 Apr-9 Apr
Week 15: 12 Apr-16 Apr
Week 16: 19 Apr-23 Apr
Week 17: 26 Apr-30 Apr